## QA Test Cases
QA Test Report — WhatsApp Automation / CRM SaaS Platform
Tested 2026-07-24 · admin@demo.com (TENANT_OWNER) · http://localhost:3000
Yellow rows = work completed in this pass (defect fixed or feature added). Unfilled rows = existing behaviour re-verified, no change made.
Module | Flow | Page/Screen | Test Scenario | Expected Result | Actual/Current Result | Status | Logged In As | Issue Found In | Tested Date | URL | Remarks | Test Remarks | Final Test Remarks & Solution Applied
Authentication | Login | Login | Valid credentials sign in | Session created, user returned | Session created, user returned | Pass | admin@demo.com | — | 2026-07-24 | /login | NextAuth v5 credentials | Verified via /api/auth/session | No change needed.
Authentication | Route guard | All API routes | 18 API routes called with no session | All return 401 | All 18 returned 401 | Pass | (anonymous) | — | 2026-07-24 | /api/* | Includes new /api/quick-replies | /api/messages is POST-only; GET correctly 405 | No change needed. Auth boundary intact.
Authentication | Public routes | Auth endpoints | register / forgot-password / reset-password reachable unauthenticated | Reachable | Reachable | Pass | (anonymous) | — | 2026-07-24 | /api/auth/* | Only 4 public routes by design | Correct and intentional | No change needed.
Authentication | Signup gate | Register | Submit the signup form while SIGNUP_ACCESS_TOKEN is configured | Account created | Every submission returned 403 "Invalid access token" — the page had no access-token field and never sent one, so /register was completely unusable | Fail → Fixed → Pass | (anonymous) | app/(auth)/register/page.tsx | 2026-07-24 | /register | CRITICAL — onboarding entirely blocked on this page | Only /login → Sign up worked; found during live browser testing | Fixed. Added the Access token field and included it in the payload. Two workspaces registered live through the form afterwards.
Authentication | Duplicate signup | Register | Register again with an existing email | Rejected; exactly one user row | Rejected; 1 row | Pass | (anonymous) | — | 2026-07-24 | /register | — | Verified in browser | No change needed.
Authentication | Wrong password | Login | Sign in with an incorrect password | Refused, kept on login | Refused, still on /login | Pass | (anonymous) | — | 2026-07-24 | /login | — | Verified in browser | No change needed.
Authentication | Sign out | App shell | Sign out, then call a protected API | 401 once session is gone | 401 | Pass | generated account | — | 2026-07-24 | /api/auth/signout | — | Verified in browser | No change needed.
Multi-tenancy | Isolation — reads | All modules | Foreign workspace's contact/lead/conversation/campaign fetched by ID | 404, indistinguishable from missing | 404 on all 4 | Pass | admin@demo.com | — | 2026-07-24 | /api/{contacts,leads,conversations,campaigns}/[id] | Seeded a second real tenant | No 403 leak confirming the row exists | No change needed.
Multi-tenancy | Isolation — writes | All modules | 8 PATCH/DELETE attempts on foreign rows | 404, rows untouched | 404 on all 8; all rows survived unmodified | Pass | admin@demo.com | — | 2026-07-24 | /api/* | Contact, lead, conversation, ticket, quick reply, campaign | Re-read from DB to confirm no mutation | No change needed.
Multi-tenancy | Isolation — lists | All modules | 7 list/search endpoints scanned for foreign IDs | No foreign row present | None present | Pass | admin@demo.com | — | 2026-07-24 | /api/* | Includes global search | Raw response bodies string-searched for IDs | No change needed.
Multi-tenancy | Isolation — AI | Inbox | AI qualify/summarize/sentiment on a foreign conversation | 404 before any model call | 404 on all 3 | Pass | admin@demo.com | — | 2026-07-24 | /api/ai/* | Guard runs before the billable call | New sentiment route inherits the guard | No change needed.
Multi-tenancy | Isolation — browser | Cross-session | Workspace B requests Workspace A's contact by ID | 404 | 404 | Pass | generated account B | — | 2026-07-24 | /api/contacts/[id] | Two real browser sessions | Verified in the live UI run | No change needed.
WhatsApp Inbound | Webhook security | — | POST without X-Hub-Signature-256 | 403 | 403 | Pass | (Meta) | — | 2026-07-24 | /api/webhook/whatsapp | HMAC over raw body | Fails closed if the secret is unset | No change needed.
WhatsApp Inbound | Webhook verify | — | GET with a wrong hub.verify_token | 403 | 403 | Pass | (Meta) | — | 2026-07-24 | /api/webhook/whatsapp | — | — | No change needed.
WhatsApp Inbound | Message ingestion | Inbox | Inbound message for a tenant configured via Settings with no matching Business record | Contact + conversation created, message stored | Every inbound message was dropped — FK violation contacts_businessId_fkey, logged and swallowed with a 200 to Meta | Fail → Fixed → Pass | (Meta) | app/api/webhook/whatsapp/route.ts:249 | 2026-07-24 | /api/webhook/whatsapp | CRITICAL — silent total message loss | Root cause: a synthesised ID biz_${tenantId} that no businesses row has | Fixed. Fallback now calls the existing ensureDefaultBusiness(tenantId) service. Re-tested: message ingested, conversation created.
WhatsApp Inbound | Contact creation | Inbox | First message from an unknown number | Contact auto-created with profile name | Created correctly | Pass *(regression)* | (Meta) | — | 2026-07-24 | /api/webhook/whatsapp | — | — | No change needed.
WhatsApp Inbound | Duplicate delivery | Inbox | Meta redelivers the same message ID | Stored once, counters not double-incremented | Handled once | Pass *(regression)* | (Meta) | — | 2026-07-24 | /api/webhook/whatsapp | P2002 path | — | No change needed.
WhatsApp Status | Message receipts | Inbox | delivered then read for an agent message | Ladder SENT→DELIVERED→READ | Ladder followed | Pass *(regression)* | (Meta) | — | 2026-07-24 | /api/webhook/whatsapp | — | — | No change needed.
WhatsApp Status | Out-of-order receipt | Inbox | delivered arrives after read | READ not walked backwards | Remained READ | Pass *(regression)* | (Meta) | — | 2026-07-24 | /api/webhook/whatsapp | Monotonic STATUS_RANK | — | No change needed.
Campaigns | Delivery tracking | Campaigns | Meta delivered receipt for a campaign recipient | deliveredAt stamped, deliveredCount +1 | Impossible — nothing correlated Meta's message ID to a recipient, so deliveredAt/readAt/repliedAt could never be filled | Fail → Fixed → Pass | admin@demo.com | CampaignContact model + both send paths | 2026-07-24 | /api/webhook/whatsapp | CRITICAL — PRD campaign analytics unachievable | Both send paths discarded Meta's response; campaign sends write no Message row | Fixed with the approved additive column CampaignContact.waMessageId. Both send paths persist Meta's ID; the webhook correlates receipts back.
Campaigns | Delivery — duplicate | Campaigns | Same delivered receipt redelivered | Counter stays at 1 | Stayed at 1 | Pass | admin@demo.com | — | 2026-07-24 | /api/webhook/whatsapp | First-write-wins, null-guarded | Stamp + counter in one transaction | Fix verified — no counter inflation.
Campaigns | Delivery — read implies delivered | Campaigns | read arrives with no prior delivered | Both timestamps stamped | Both stamped; both counters +1 | Pass | admin@demo.com | — | 2026-07-24 | /api/webhook/whatsapp | Meta emits out of order | — | Fix verified.
Campaigns | Delivery — foreign receipt | Campaigns | Another tenant's number sends a receipt for our recipient | Refused, counters untouched | Refused, untouched | Pass | (Meta) | — | 2026-07-24 | /api/webhook/whatsapp | Ownership asserted via parent campaign | A unique ID identifies, it does not authorise | Fix verified — tenant-safe.
Campaigns | Reply attribution | Campaigns | Recipient replies to a broadcast | repliedAt stamped, repliedCount +1, once only | Stamped once; 2nd message did not re-credit | Pass | (Meta) | — | 2026-07-24 | /api/webhook/whatsapp | Meta never reports "replied" | Inferred from inbound message, isNew-guarded | New capability delivered.
Campaigns | Scheduling | Campaigns | Create a campaign with a future Schedule date | Parked as SCHEDULED; nothing sent until due | Sent immediately to the entire audience — scheduledAt was validated then ignored, and the UI never sent the field | Fail → Fixed → Pass | admin@demo.com | app/api/campaigns/route.ts, app/(dashboard)/campaigns/page.tsx | 2026-07-24 | /campaigns | CRITICAL — unrecoverable; a broadcast for next week went out instantly | The cron existed but nothing ever created a SCHEDULED row | Fixed. API parks future-dated campaigns as SCHEDULED with no startedAt; UI sends an ISO instant; helper text corrected.
Campaigns | Scheduling — past date | Campaigns | Schedule date already elapsed | Treated as send-now | Sent immediately, not parked | Pass | admin@demo.com | — | 2026-07-24 | /campaigns | Matches user intent | — | Fix verified.
Campaigns | Scheduling — invalid date | Campaigns | Unparseable scheduledAt | 400, nothing sent | 400 "Invalid scheduled date" | Pass | admin@demo.com | — | 2026-07-24 | /api/campaigns | Rejected, never silently ignored | Silent-ignore would blast the audience | Fix verified.
Campaigns | Scheduled send (cron) | — | Cron processes a due campaign for a workspace with no WhatsApp credentials | Recipients recorded FAILED with a reason | Recipients were marked SENT without any send happening | Fail → Fixed → Pass | (cron) | app/api/cron/campaigns/route.ts | 2026-07-24 | /api/cron/campaigns | Surfaced only once scheduling actually worked | Also used workspace-level creds, ignoring per-business numbers | Fixed. Uses resolveWhatsAppCreds(businessId) and records FAILED with an honest reason.
Campaigns | Cron auth | — | Cron endpoint called without CRON_SECRET | 401 | 401 | Pass *(regression)* | (anonymous) | — | 2026-07-24 | /api/cron/campaigns | — | — | No change needed.
Campaigns | Cron pickup | — | Backdated SCHEDULED campaign | Picked up, moved off SCHEDULED, completed | processed: 1, moved to COMPLETED | Pass | (cron) | — | 2026-07-24 | /api/cron/campaigns | Verified with real SQL backdating | — | Fix verified end-to-end.
Campaigns | Create / validate | Campaigns | Empty name, empty message, no contacts | 400 with a specific message each | 400 on all three | Pass *(regression)* | admin@demo.com | — | 2026-07-24 | /api/campaigns | — | — | No change needed.
Campaigns | Duplicate / delete | Campaigns | Duplicate then delete a campaign | 201 then 200 | 201 then 200 | Pass *(regression)* | admin@demo.com | — | 2026-07-24 | /campaigns | — | — | No change needed.
Campaigns | Detail view | Campaign detail | Recipient delivery columns exposed | sentAt/deliveredAt/readAt/repliedAt present | All present and now populated | Pass | admin@demo.com | — | 2026-07-24 | /api/campaigns/[id] | Stale comment corrected | waMessageId deliberately not exposed | Documentation corrected alongside the fix.
Chatbot | Handoff to human | Inbox | Flow reaches a handoff node | Conversation assigned to an agent and taken off AI | Only isAiActive was cleared — thread left unassigned; the builder's team/queue/department was discarded | Fail → Fixed → Pass | (Meta) | app/api/webhook/whatsapp/route.ts | 2026-07-24 | /api/webhook/whatsapp | Handoff did not actually hand off | PRD requires human handoff to reach a person | Fixed. assignConversationToAgent() picks the least-loaded active agent, sets ASSIGNED, preserves the queue as a label. Schema-free.
Chatbot | Handoff — least loaded | Inbox | One busy agent (3 open threads), one idle | Idle agent chosen | Idle agent chosen | Pass | (Meta) | — | 2026-07-24 | /api/webhook/whatsapp | Self-correcting vs round-robin | Ties broken on ID | Fix verified.
Chatbot | Handoff — inactive agents | Inbox | Deactivated agent present | Never assigned | Never assigned | Pass | (Meta) | — | 2026-07-24 | /api/webhook/whatsapp | isActive respected | — | Fix verified.
Chatbot | Handoff — no agents | Inbox | Workspace with zero active agents | Degrade gracefully, still 200 | 200; thread left unassigned with AI off | Pass | (Meta) | — | 2026-07-24 | /api/webhook/whatsapp | Best-effort by design | Webhook must never fail on this | Fix verified.
Chatbot | Handoff — re-trigger | Inbox | Handoff fires again on an assigned thread | Existing assignee kept | Kept; label not duplicated | Pass | (Meta) | — | 2026-07-24 | /api/webhook/whatsapp | Customer not yanked mid-conversation | — | Fix verified.
Chatbot | Flow CRUD | Chatbot Builder | Create / read / validate / duplicate / delete a flow | All succeed; missing trigger 400 | All succeeded; 400 on missing trigger | Pass *(regression)* | admin@demo.com | — | 2026-07-24 | /chatbot | 9 node kinds supported | — | No change needed.
Chatbot | Multi-turn session | Inbox | Question node pauses, customer answers, flow resumes | Session persisted and resumed | Resumed correctly | Pass *(regression)* | (Meta) | — | 2026-07-24 | /api/webhook/whatsapp | activeFlowId/activeNodeId/flowVars | — | No change needed.
Chatbot | Builder — node drag | Chatbot Builder | Drag a Message node from the palette onto the canvas | Node appears on the canvas | Canvas rendered the new node | Pass | generated account A | — | 2026-07-24 | /chatbot | Real browser drag with the custom MIME payload | Live Playwright run | Verified working.
Chatbot | Builder — persistence | Chatbot Builder | Confirm the dragged node persists | Node count in DB increases | Persisted via the builder's autosave | Pass | generated account A | — | 2026-07-24 | /chatbot | Autosave is why Save sits disabled | Live Playwright run | Verified working.
Inbox | Qualify Lead (AI) | Inbox → Contact panel | Click "Qualify Lead (AI)" | Lead scored via BANT | Button did nothing — no handler, marked TODO while the endpoint existed and worked | Fail → Fixed → Pass | admin@demo.com | components/inbox/ContactPanel.tsx | 2026-07-24 | /inbox | Backend fully built, UI never connected | — | Fixed. Added useAiQualify and wired the button with pending/error states and an inline score. Endpoint returned 200.
Inbox | Summarize (AI) | Inbox → Contact panel | Click "Summarize (AI)" | Thread summary shown | Button did nothing — useAiSummarize existed but was never called | Fail → Fixed → Pass | admin@demo.com | components/inbox/ContactPanel.tsx | 2026-07-24 | /inbox | — | — | Fixed. Wired to the existing hook; summary rendered. Endpoint returned 200.
Inbox | Resolve conversation | Inbox → Contact panel | Click "Resolve" | Status → RESOLVED | Button did nothing | Fail → Fixed → Pass | admin@demo.com | components/inbox/ContactPanel.tsx | 2026-07-24 | /inbox | — | — | Fixed. Wired to useResolveConversation; disables once resolved. PATCH verified 200 + persisted.
Inbox | Assign agent | Inbox → Contact panel | Pick an agent from the dropdown | Conversation assigned | Dropdown did nothing — and the hook typed assignedToId, which the API's strictObject rejects | Fail → Fixed → Pass | admin@demo.com | components/inbox/ContactPanel.tsx, hooks/useMessages.ts | 2026-07-24 | /inbox | Two defects in one flow | Confirmed: assignedToId → 400; assigneeId → 200 | Fixed. Corrected the hook contract to assigneeId and wired the select with rollback on error.
Inbox | Sentiment (AI) | Inbox → Contact panel | Check customer sentiment | Verdict returned | No way to reach it — detectSentiment() existed in lib/ai.ts with zero callers, no route, no UI | Missing → Added → Pass | admin@demo.com | lib/ai.ts (orphaned) | 2026-07-24 | /inbox | PRD AI feature unreachable | — | Added /api/ai/sentiment (tenant-guarded, read-only, last 10 inbound messages) + hook + button. Returned a live verdict.
Inbox | Quick replies — picker | Inbox composer | Type / in the composer | Matching canned replies listed, selection inserts text | Picker opens, filters, inserts | Missing → Added → Pass | admin@demo.com | — | 2026-07-24 | /inbox | QuickReply model existed with zero API/UI/hooks | Keyboard ↑/↓/Enter/Tab/Esc handled | Added. Enter is intercepted so the raw /shortcode can never be sent as a message.
Inbox | Attachment drag | Inbox | Drag a file over the conversation area | Drop target responds | Drop target responded | Pass | generated account A | — | 2026-07-24 | /inbox | Live Playwright run | — | Verified working.
Quick Replies | Create | Settings → Quick Replies | Create /QA-Hours | Saved, shortcode normalised | Saved as qa-hours | Missing → Added → Pass | admin@demo.com | — | 2026-07-24 | /settings | New /api/quick-replies | Leading slash stripped, lower-cased | Added. Full CRUD API + hook + settings tab.
Quick Replies | Duplicate | Settings → Quick Replies | Same shortcode twice | 409 | 409 | Pass | admin@demo.com | — | 2026-07-24 | /api/quick-replies | Matches the model's unique constraint | A validation result, not a 500 | Verified.
Quick Replies | Validation | Settings → Quick Replies | Spaces/symbols in shortcode; empty content; malformed JSON | 400 each | 400 on all three | Pass | admin@demo.com | — | 2026-07-24 | /api/quick-replies | — | — | Verified.
Quick Replies | Update / delete | Settings → Quick Replies | PATCH content, PATCH empty body, PATCH/DELETE unknown ID, DELETE | 200 / 400 / 404 / 404 / 200 | Exactly as expected; row gone from list | Pass | admin@demo.com | — | 2026-07-24 | /api/quick-replies/[id] | — | Business-scoped lookup | Verified.
Quick Replies | Create via UI | Settings → Quick Replies | Create a quick reply in the browser | Persisted and listed | Persisted, verified in DB | Pass | generated account A | — | 2026-07-24 | /settings | Live Playwright run | — | Verified working.
Contacts | Create / validate | Contacts | Create, duplicate phone, missing phone | 201 / 409 / 400 | 201 / 409 / 400 | Pass *(regression)* | admin@demo.com | — | 2026-07-24 | /contacts | — | — | No change needed.
Contacts | Read / update / delete | Contacts | GET, PATCH, DELETE by ID | All 200 | All 200 | Pass *(regression)* | admin@demo.com | — | 2026-07-24 | /contacts | — | — | No change needed.
Contacts | Soft delete | Contacts | Deleted contact absent from list | Removed from list, record retained | Removed; record retained | Pass *(regression)* | admin@demo.com | — | 2026-07-24 | /api/contacts | Deliberate soft delete (isBlocked) | Initially flagged as a bug; confirmed intentional | No change needed — by design.
Contacts | Export | Contacts | Export contacts | 200 CSV | 200 | Pass *(regression)* | admin@demo.com | — | 2026-07-24 | /api/contacts/export | — | — | No change needed.
Contacts | Import | Contacts | Valid / invalid / duplicate / empty rows classified | Correctly bucketed | Correctly bucketed | Pass *(regression)* | admin@demo.com | — | 2026-07-24 | /contacts | SheetJS client-side parse | — | No change needed.
Contacts | Create via UI | Contacts | Create a contact through the Add Contact modal | Persisted with every field | Persisted; verified in DB | Pass | generated account A/B | — | 2026-07-24 | /contacts | Live Playwright run, random data | Appeared in the list with no reload | Verified working.
Contacts | Form validation via UI | Contacts | Submit the contact form with every field empty | Blocked with visible messages | Blocked, nothing saved | Pass | generated account A | — | 2026-07-24 | /contacts | Live Playwright run | — | Verified working.
Leads | Create | Leads | Create with contactId + title | 201, default stage assigned | 201, stageId auto-assigned | Pass *(regression)* | admin@demo.com | — | 2026-07-24 | /leads | — | — | No change needed.
Leads | Validation | Leads | Foreign contact / missing title / score 150 | 404 / 400 / 400 | 404 / 400 / 400 | Pass *(regression)* | admin@demo.com | — | 2026-07-24 | /api/leads | — | — | No change needed.
Leads | Update / delete | Leads | PATCH then DELETE, then GET | 200 / 200 / 404 | 200 / 200 / 404 | Pass *(regression)* | admin@demo.com | — | 2026-07-24 | /leads | — | — | No change needed.
Leads | Scoring bands | Leads | 0–30 / 31–60 / 61–80 / 81–100 | COLD / WARM / HOT / QUALIFIED | Exactly as the PRD specifies | Pass *(regression)* | admin@demo.com | — | 2026-07-24 | /leads | — | — | No change needed.
Leads | Export | Leads | Export leads | 200 | 200 | Pass *(regression)* | admin@demo.com | — | 2026-07-24 | /api/leads/export | — | — | No change needed.
Pipeline | Stage provisioning | Settings → Lead Pipeline | Tenant auto-provisioned with 7 stages, exactly 1 default | 7 stages, 1 default | 7 stages, 1 default | Pass *(regression)* | admin@demo.com | — | 2026-07-24 | /settings | Dynamic PipelineStage | Admin-gated tab | No change needed.
Pipeline | Drag to reorder | Settings → Lead Pipeline | Drag stage 1 onto position 3 and save | Order changes and persists | Order changed and persisted to the database | Pass | generated account A | — | 2026-07-24 | /settings | Live Playwright HTML5 drag | Save enables only when the list is dirty | Verified working.
Tickets | Create | Tickets | Create with subject + priority | 201, slaDeadline derived from priority | 201 with derived deadline | Pass *(regression)* | admin@demo.com | — | 2026-07-24 | /tickets | Deadline derived, never client-supplied | — | No change needed.
Tickets | Strict validation | Tickets | Body carrying status or unknown keys | 400 | 400 "Unrecognized key" | Pass *(regression)* | admin@demo.com | — | 2026-07-24 | /api/tickets | Prevents opening a pre-resolved ticket | — | No change needed.
Tickets | Lifecycle | Tickets | PATCH status, invalid status, unknown ID | 200 / 400 / 404 | 200 / 400 / 404 | Pass *(regression)* | admin@demo.com | — | 2026-07-24 | /tickets | — | — | No change needed.
Tickets | Dead client hooks | — | useTicket(id) / useDeleteTicket() | Should not exist — API exposes PATCH only, by documented decision | Both existed and would have returned 405 on first use | Fail → Fixed → Pass | admin@demo.com | hooks/useTickets.ts | 2026-07-24 | — | Latent trap for the next developer | Neither had a UI caller, so nothing was visibly broken | Fixed by removal, with a comment explaining why GET/DELETE are withheld.
Tickets | SLA display | Tickets | SLA countdown / breach shown per ticket | Rendered | Rendered via SlaCell | Pass *(regression)* | admin@demo.com | — | 2026-07-24 | /tickets | — | Escalation automation not built — see §5 | No change needed for display.
Templates | Create / validate | Templates | Create, duplicate name, invalid category | 201 / 409 / 400 | 201 / 409 / 400 | Pass *(regression)* | admin@demo.com | — | 2026-07-24 | /templates | — | — | No change needed.
Analytics | Dashboard data | Analytics | Fetch analytics | 200 with aggregates | 200 | Pass *(regression)* | admin@demo.com | — | 2026-07-24 | /analytics | — | — | No change needed.
Knowledge Base | RAG chunking | Knowledge Base | Chunk realistic prose | Multiple overlapping chunks | 20 chunks | Pass *(regression)* | admin@demo.com | — | 2026-07-24 | /knowledge-base | Qdrant + embeddings | — | No change needed.
Knowledge Base | CRUD | Knowledge Base | List / fetch / delete docs | 200 | 200 | Pass *(regression)* | admin@demo.com | — | 2026-07-24 | /api/knowledge | Vectors deleted alongside | — | No change needed.
Team | Listing | Team | List team members | 200 | 200 | Pass *(regression)* | admin@demo.com | — | 2026-07-24 | /team | — | — | No change needed.
Settings | Tabs | Settings | General / WhatsApp / Billing / Notifications load and save | 200 | 200 | Pass *(regression)* | admin@demo.com | — | 2026-07-24 | /settings | — | Quick Replies tab added alongside | No change needed.
Billing | Plans | Billing | List plans | 200 | 200 | Pass *(regression)* | admin@demo.com | — | 2026-07-24 | /billing | Stripe | Razorpay unimplemented — see §5 | No change needed.
Businesses | Multi-business | Businesses | List / switch business | 200 | 200 | Pass *(regression)* | admin@demo.com | — | 2026-07-24 | /businesses | — | — | No change needed.
Search | Global search | All | Search across entities | 200, tenant-scoped | 200, no foreign rows | Pass *(regression)* | admin@demo.com | — | 2026-07-24 | /api/search | — | — | No change needed.
Notifications | Feed | Header | Fetch notifications | 200 | 200 | Pass *(regression)* | admin@demo.com | — | 2026-07-24 | /api/notifications | Audit log + recent messages | — | No change needed.
Navigation | All pages | 13 dashboard pages | Open each page with an authenticated session | 200, stays on route, no runtime errors | All 13 rendered clean | Pass | generated account A | — | 2026-07-24 | /dashboard … /billing | Live Playwright run | Asserted final URL, not just status | No change needed.
Build & Types | Regression gate | — | tsc --noEmit, next build, eslint | 0 type errors, build succeeds, no new lint errors | 0 errors; compiled successfully; 8 pre-existing lint errors, none in changed files | Pass | — | — | 2026-07-24 | — | Full-project gate | Pre-existing errors are in untouched files | No regressions introduced.

## Defects Fixed
Defects Found & Fixed — all rows completed
# | Severity | Area | Defect | Solution applied | Status
3.1 | CRITICAL | WhatsApp Inbound | Every inbound message dropped for tenants configured via Settings — a synthesised business ID violated a foreign key, and the 200 to Meta meant no retry. | Fallback now calls the existing ensureDefaultBusiness() service, resolving to a real row. | Fixed & verified
3.2 | CRITICAL | Campaigns | Scheduled campaigns sent immediately — the form never sent scheduledAt and the API ignored it; the cron could never find work. | API parks future-dated campaigns as SCHEDULED; UI sends an ISO instant; invalid dates rejected with 400. | Fixed & verified
3.3 | CRITICAL | Campaigns | Delivery tracking impossible — nothing correlated Meta's message ID to a recipient, so delivered/read/replied could never be filled. | Approved additive column CampaignContact.waMessageId; both send paths persist it; webhook attributes receipts and counters. | Fixed & verified
3.4 | HIGH | Chatbot | Handoff did not hand off — only cleared the AI flag, leaving the thread unassigned; the configured team/queue was discarded. | Assigns the least-loaded active agent, sets ASSIGNED, preserves the queue as a label. Schema-free. | Fixed & verified
3.5 | HIGH | Inbox | Four quick actions inert — Qualify, Summarize, Resolve and agent assignment were all TODO stubs over working backends. | All four wired to hooks with pending/error states and in-panel results. | Fixed & verified
3.6 | HIGH | Inbox | Conversation-assignment hook typed assignedToId while the API's strictObject accepts assigneeId — it could never have worked. | Corrected the hook contract to assigneeId. | Fixed & verified
3.7 | MEDIUM | Campaigns | Cron marked recipients SENT with no WhatsApp credentials — reporting a broadcast nobody received. | Uses resolveWhatsAppCreds(businessId) and records FAILED with an explicit reason. | Fixed & verified
3.8 | LOW | Tickets | Dead hooks useTicket/useDeleteTicket called endpoints the API deliberately withholds; both would 405. | Removed, with a comment recording why those methods are withheld. | Fixed & verified
3.9 | LOW | Docs | Two stale comments contradicted the code they described. | Corrected in campaigns/[id] and the webhook header. | Fixed & verified
4.0 | CRITICAL | Authentication | /register was unusable — no access-token field and none sent, so every signup returned 403 while the invite gate was on. Found during live UI testing. | Added the Access token field and included it in the payload; registration verified end-to-end. | Fixed & verified

## Features Added
Features Delivered — all rows completed
# | Feature | What was built | Verified by | Status
1 | Quick Replies | Full CRUD API (/api/quick-replies + [id]), React Query hook, Settings tab, and a "/shortcode" picker in the inbox composer with keyboard navigation. | 13 API scenarios + live UI creation and picker test | Completed
2 | AI Sentiment | /api/ai/sentiment reaching detectSentiment(), which had existed in lib/ai.ts with no caller, plus a hook and inbox button. | Returned a live verdict; 404/401/400 guards checked | Completed
3 | Campaign delivery tracking | Meta message-ID correlation end to end: persisted on send, attributed on receipt, with delivered/read/replied counters. | 24/24 assertions incl. duplicate and out-of-order receipts | Completed
4 | Campaign scheduling | Future-dated campaigns park as SCHEDULED and are sent by the existing cron. | Verified with a backdated campaign through the cron | Completed
5 | Conversation routing on handoff | Least-loaded agent assignment with queue preserved as a label. | 13/13 assertions | Completed
6 | Signup access-token field | Access token field on /register, included in the registration payload. | Two workspaces registered live through the form | Completed

## Live UI Run
Live UI End-to-End Run (Playwright, random data) — 2026-07-24
32 passed / 0 failed across 32 steps
Generated login credentials
Workspace | Full name | Email (login) | Password | Role | Tenant ID
Zephyr Exports 9belkg | Arjun Verma | arjun.verma.t9go4u@qa-probe.test | Qa3ac0vj239!F7 | TENANT_OWNER | cmryyfqus005ftiu7g99c0yyc
Quanta Technologies 1r2nvw | Rajesh Iyer | rajesh.iyer.37ukwu@qa-probe.test | Qa1oh87t654!UR | TENANT_OWNER | cmryyii5i005vtiu7ezc7ml91
Records created through the UI
Type | Name | Detail | Database ID
Contact | Vikram Iyer | 912356498685 / vikram.iyer.5acsjk@vertex.in | cmryygq1n005rtiu7g09vte4z
Contact | Aditya Menon | 917343689093 / aditya.menon.9pie2i@quanta.in | cmryyj15n0061tiu7d4iihxrn
Quick Reply | /qac81rlq | Thanks for reaching out! Our team replies within 8 hours. | cmryyh3ep005ttiu7syb4uti3
Chatbot Flow | QA Flow u9sxvl | created via builder UI, Message node dragged in | cmryyi5lm005utiu7yyor4dvx
Step-by-step results
# | Area | Layer exercised | Action | Random data used | Status
1 | Authentication | Frontend + Backend + DB | Register workspace through the signup form (Workspace A) | randomly generated | Pass
2 | Authentication | Frontend + Backend + DB | Sign in with the generated credentials (Workspace A) | randomly generated | Pass
3 | Navigation | Frontend + Backend + DB | Open Dashboard and render | randomly generated | Pass
4 | Navigation | Frontend + Backend + DB | Open Inbox and render | randomly generated | Pass
5 | Navigation | Frontend + Backend + DB | Open Contacts and render | randomly generated | Pass
6 | Navigation | Frontend + Backend + DB | Open Leads and render | randomly generated | Pass
7 | Navigation | Frontend + Backend + DB | Open Campaigns and render | randomly generated | Pass
8 | Navigation | Frontend + Backend + DB | Open Chatbot and render | randomly generated | Pass
9 | Navigation | Frontend + Backend + DB | Open Tickets and render | randomly generated | Pass
10 | Navigation | Frontend + Backend + DB | Open Knowledge Base and render | randomly generated | Pass
11 | Navigation | Frontend + Backend + DB | Open Analytics and render | randomly generated | Pass
12 | Navigation | Frontend + Backend + DB | Open Team and render | randomly generated | Pass
13 | Navigation | Frontend + Backend + DB | Open Businesses and render | randomly generated | Pass
14 | Navigation | Frontend + Backend + DB | Open Settings and render | randomly generated | Pass
15 | Navigation | Frontend + Backend + DB | Open Billing and render | randomly generated | Pass
16 | Contacts | Frontend + Backend + DB | Create a contact through the Add Contact modal | randomly generated | Pass
17 | Contacts | Frontend + Backend + DB | New contact appears in the list without a page reload | randomly generated | Pass
18 | Contacts | Frontend + Backend + DB | Submit the contact form with every field empty | randomly generated | Pass
19 | Quick Replies | Frontend + Backend + DB | Create a quick reply through the new settings tab | randomly generated | Pass
20 | Inbox | Frontend + Backend + DB | Open the quick-reply picker by typing / in the composer | randomly generated | Pass
21 | Pipeline (Drag & Drop) | Frontend + Backend + DB | Drag stage 1 onto position 3 and save | randomly generated | Pass
22 | Chatbot (Drag & Drop) | Frontend + Backend + DB | Drag a Message node from the palette onto the builder canvas | randomly generated | Pass
23 | Chatbot (Drag & Drop) | Frontend + Backend + DB | Confirm the dragged node persisted (builder autosave) | randomly generated | Pass
24 | Inbox (Drag & Drop) | Frontend + Backend + DB | Drag a file over the conversation area | randomly generated | Pass
25 | Authentication | Frontend + Backend + DB | Register workspace through the signup form (Workspace B) | randomly generated | Pass
26 | Authentication | Frontend + Backend + DB | Sign in with the generated credentials (Workspace B) | randomly generated | Pass
27 | Contacts | Frontend + Backend + DB | Create a contact through the Add Contact modal (Workspace B) | randomly generated | Pass
28 | Contacts | Frontend + Backend + DB | New contact appears in the list without a page reload (Workspace B) | randomly generated | Pass
29 | Security / Multi-tenancy | Frontend + Backend + DB | Workspace B requests Workspace A's contact by ID | randomly generated | Pass
30 | Authentication | Frontend + Backend + DB | Sign out, then call a protected API from the same browser | randomly generated | Pass
31 | Authentication | Frontend + Backend + DB | Register again with an email that already exists | randomly generated | Pass
32 | Authentication | Frontend + Backend + DB | Sign in with a wrong password | randomly generated | Pass

## Remaining
Not Done — open recommendations (deliberately not implemented)
# | Item | Why not done | Schema change needed?
1 | Department / skill-based routing | Needs User.department / User.skills columns. Schema change not approved, so not made. Handoff routes least-loaded and keeps the requested queue as a label. | Yes (additive)
2 | GST invoicing with GSTIN | Needs Tenant.gstin. Not approved, not made. | Yes (additive)
3 | Ticket SLA escalation automation | SLA deadlines are derived, stored and displayed with breach state. Escalation automation was my own suggestion, not a confirmed PRD requirement, so it was not built. | No
4 | Razorpay payments | Columns exist; only Stripe is wired. Out of scope for this pass. | No
5 | Revenue page mock rows | Two hardcoded preview transactions remain as a fallback; the real API exists. | No
6 | Pre-existing lint errors (8) | All in files untouched by this pass. Fixing them means editing modules outside the audit scope. | No